## Sheet1
TASK : | WHO ? | ESTIMATED TIME | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | TOTAL TIME | ERROR
Make a Tasks List | Ophelie | 2h |  |  | 1h |  |  | 1h | 1h
Sprint Backlog of features/requirements | Ophelie | 2h | 30mn |  |  | 1h |  | 1h30 | 30mn
UML design model | Paul | 2h |  |  |  |  | 50mn | 50mn | 1h10
Main Code (Instructions) | Antoine | 1h |  | 45mn |  |  |  | 45mn | 15mn
Adding Sound | Antoine | 4h |  |  |  | 2h |  | 2h | 2h
QR Code Image | Antoine | 1h | 10mn |  |  |  |  | 10mn | 50mn
GUI Code | Antoine | 1d |  |  | 1d | 1d |  | 2d | -1d
Unit Tests | Ophelie | 1h |  |  |  |  | 1h | 1h | 0
Verification UML diagram | Paul | 1h |  |  |  |  | 20mn | 20mn | 40mn
Put the code on Github | Antoine | 1h |  |  |  |  | 1h | 1h | 0
|  |  |  | 5 | 0
|  |  |  | 4 | 10
|  |  |  | 3 | 30
|  |  |  | 2 | 90
|  |  |  | 1 | 100
|  |  |  | 0 | 100
|  |  |  | 5 | 0
|  |  |  | 4 | 20
|  |  |  | 3 | 40
|  |  |  | 2 | 60
|  |  |  | 1 | 80
|  |  |  | 0 | 100